## Sheet1
|  | Feb |  | Mar |  |  |  | Apr |  |  |  |  | May | [7 empty] | Jun |  |  |  | Jul | [16 empty] | Aug
Milestones |  | 19 | 26 | 04 | 11 | 18 | 25 | 01 | 08 | 15 | 22 | 29 | 04 | 05 | 06 | 07 | 08 | 13 | 20 | 27 | 03 | 10 | 17 | 24 | 01 | 08 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 03 | 04 | 05 | 06 | 07 | 10 | 11 | 12 | 13 | 14
1. Project Plan
2. Initial Implementation of the CNN
3. Operating System set up
4. Working Implementation of the CNN
5. Back-End implemented
6. System verified
7. Demonstrator fully set up
8. Bachelor Thesis and Working Repository
|  | Feb |  | Mar |  |  |  | Apr |  |  |  |  | May | [7 empty] | Jun |  |  |  | Jul | [16 empty] | Aug
Process | MH | 19 | 26 | 04 | 11 | 18 | 25 | 01 | 08 | 15 | 22 | 29 | 04 | 05 | 06 | 07 | 08 | 13 | 20 | 27 | 03 | 10 | 17 | 24 | 01 | 08 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 03 | 04 | 05 | 06 | 07 | 10 | 11 | 12 | 13 | 14
1. Administration | 240
1.1 Project Plan | 26 |  | 10 | 16
1.2 Bachelor Thesis | 214 |  |  |  |  | 4 | 4 | 4 | 2 |  | 2 | [5 empty] | 2 | 2 |  | 8 | [7 empty] | 3 | 8 |  | 3 | 8 | 4 | [8 empty] | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
2. Training | 151 | [8 empty] | Holidays | [12 empty] | Exams
2.1 Research | 37 | 8 | 3 |  |  | 6 | 6 | 6 | [7 empty] | 4 | 4
2.2 Determine CNN Architecture | 36 | [7 empty] | 8 |  | 8 | 8 | [8 empty] | 4 | [5 empty] | 4 |  |  | 4
2.3 Define Training Dataset | 5 | [11 empty] | 2 | [7 empty] | 1 | [5 empty] | 1 |  |  | 1
2.4 Train Model | 28 | [11 empty] | 6 | 8 | 8 | [5 empty] | 2 | [5 empty] | 2 |  |  | 2
2.5 Verify Accuracy | 45 | [14 empty] | 4 | 4 | 8 | 8 |  | 1 | 8 |  |  |  |  | 1 | 5 |  | 1 | 5
3. Inference | 329 | [8 empty] | Holidays | [12 empty] | Exams
3.1 Research | 75
3.1.1 Toolchain and Operating System | 51 | 8 | 3 |  | 16 | 6 | 6 | 4 |  |  |  |  | 8
3.1.2 Resource Allocation (PL, Memory) | 12 | [15 empty] | 6 | 6
3.1.3 Inference API | 12 | [17 empty] | 4 | 4 | [7 empty] | 4
3.2 Set Up Operating System | 22 | [6 empty] | 2 | 6 |  | 6 | 8
3.3 Implement DPU IP | 28 | [12 empty] | 8 | 8 | 8 | [15 empty] | 4
3.4 Implement Control System | 36 | [17 empty] | 4 | 4 | 8 | 8 |  |  |  |  | 8 |  |  |  |  | 4
3.5 Implement Image Acquisition | 16 | [26 empty] | 4 | 8 | 4
3.6 Verification | 48
3.6.1 Performance | 32 | [28 empty] | 4 | 8 |  | 12 | 8
3.6.2 Accuracy (Compared to 2.5) | 16 | [33 empty] | 8 | 8
3.7 Implement User Interface | 40 | [32 empty] | 8 | 8 | 8 | 16
3.8 Reserve Time | 64 | [36 empty] | 16 | 16 | 16 | 16
Total | 720 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 |  |  |  |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16